## Slide 1
MARKETING STRATEGY
Red Chili
Social, Content & Community
Year-1 channel strategy, content pillars, influencer plan, and KPI framework — built around Dr. Khan's marketing budget commitment.
Prepared by: NTT Groups · in collaboration with Pixel Prism
DRAFT v1.0 · For Dr. Sharouz Khan and authorised reviewers only

## Slide 2
Executive Summary
What this strategy is — and what it isn't.
WHAT THIS STRATEGY IS
A Year-1 plan 12-month content calendar + channel mix anchored to a SAR 720K-960K budget.
Operationally executable Specific weekly cadence, owner per task, KPI per channel.
Aligned with the platform Loyalty hooks, e-catering enquiries, dynamic-menu promotions all flow back into the ERP.
Honest about limits Marketing amplifies a great restaurant; it does not rescue a struggling one.
WHAT THIS STRATEGY IS NOT
A virality plan We don't bet on going viral. We bet on sustained reach + conversion.
A brand reposition If brand perception is broken, that's an F&B + service issue. Marketing can't paint over it.
A guarantee of growth Marketing without product quality + ops execution = expensive. We measure honestly.
An influencer free-for-all Every influencer collab is tracked, capped, and ROI-measured. No exceptions.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
2 / 18

## Slide 3
Audience — Who We're Marketing To
Three primary segments, three different channels, three different content types.
Saudi Elite Families
35-55 · 60% of focus
WHY THEY MATTER
Special-occasion dining. Wedding catering. Corporate hospitality.
WHERE WE REACH THEM
Instagram, WhatsApp, word-of-mouth in established networks
KEY MESSAGE
'A place worthy of your guests' — heritage, plating, private dining
Expat Professionals
28-45 · 30% of focus
WHY THEY MATTER
Weekly family meals out, Friday brunches, group dinners with colleagues
WHERE WE REACH THEM
Instagram, TikTok, Google reviews, food-blog reviews
KEY MESSAGE
'Authentic Indian, no corners cut' — recipe stories, chef spotlights
Embassy & Corporate Procurement
B2B segment · 10% of focus
WHY THEY MATTER
Catering for events, receptions, multi-day functions
WHERE WE REACH THEM
LinkedIn, direct outreach, Diplomatic Quarter network
KEY MESSAGE
'Discreet, reliable, premium' — case studies, trust signals
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
3 / 18

## Slide 4
The Budget — Where SAR 720K Goes
Year 1. Adjust scale-up in Year 2 based on Year 1 KPIs.
Category
Annual SAR
% Mix
Purpose
Pixel Prism (Agency)
SAR 180,000
25%
Reels, photo, brand campaigns. Quarterly retainer.
Micro-Influencers
SAR 150,000
21%
8-15 KSA food creators per quarter. Tracked.
Paid Social & Search
SAR 120,000
17%
Meta + TikTok + Google. Geo-targeted Riyadh + Jeddah.
In-house FTEs (2)
SAR 240,000
33%
Community manager + content lead. SAR 10K/mo each.
PR / Events
SAR 30,000
4%
Soft launches, embassy outreach, industry press.
TOTAL YEAR 1 MARKETING BUDGET
SAR 720,000
100%
⚠ WORKING ASSUMPTION If Dr. Khan can commit a higher budget (SAR 960K-1.0M Year 1), increase paid social & micro-influencer spend proportionally — these are the most scalable channels. If budget is lower, cut paid social first; keep agency + FTEs intact.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
4 / 18

## Slide 5
Channel Strategy — Where We Show Up
Each channel has a distinct role. We don't post the same content everywhere.
Instagram
Primary brand stage
Reels (40%), photos (35%), stories (25%). Restaurant ambience, dishes, behind-the-scenes.
TikTok
Discovery + youth
Short-form video. Recipe origin stories, chef portraits, 'making of' content.
WhatsApp Business
1-1 conversion + loyalty
Reservations, catering enquiries, loyalty wallet updates, win-back messages. Highest ROI.
Google (Maps + Search)
Discovery for new visitors
Reviews management, GBP photos, paid search for 'Indian restaurant Riyadh' terms.
LinkedIn
B2B catering only
Embassy + corporate procurement decision-makers. Case studies, hospitality content.
Snapchat
Geo-burst for openings/events
Geofilters at flagship + during events. Limited — KSA Snap is shrinking.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
5 / 18

## Slide 6
Content Pillars — What We Post About
Five pillars. Every piece of content we make fits one of these. If it doesn't, we don't make it.
01
The Dish
35% of feed
Hero food content. The biryani, the karahi, the slow lift of the lid. Plating, steam, golden-hour shots.
02
The Heritage
20% of feed
Recipe origin stories. The grandmothers, the regions, the rituals. Why this dish exists.
03
The People
20% of feed
The chefs. The waiters. The customer who's been coming for 10 years. Faces, hands, stories.
04
The Occasion
15% of feed
Birthdays at Red Chili. Family Friday lunch. Embassy catering moments. Real customers, real moments.
05
The Offer
10% of feed
Loyalty club, e-catering enquiries, seasonal menus. The only directly transactional content. Capped at 10%.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
6 / 18

## Slide 7
Weekly Cadence — Realistic Volume
Two FTEs + Pixel Prism support produce this. We don't promise 'daily content'; we promise consistent quality.
Channel
Mon
Tue
Wed
Thu
Fri
Sat
Sun
Weekly
Instagram feed
1
—
1
—
1
1
—
4 posts
Instagram reels
—
1
—
1
—
—
1
3 reels
Instagram stories
2-3
2-3
2-3
2-3
2-3
2-3
2-3
15-20
TikTok
—
1
—
—
1
—
—
2 videos
WhatsApp blast
—
—
1
—
—
—
—
1 (loyalty)
Google updates
—
—
—
—
—
—
1
1 post
OWNER
Content Lead
Pixel Prism
Comm Mgr
Pixel Prism
Comm Mgr
Comm Mgr
⚠ WORKING ASSUMPTION Quality > volume. We'd rather post 4 strong reels per week than 14 mediocre ones. Rule: any post that doesn't match brand voice gets killed before publishing.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
7 / 18

## Slide 8
Micro-Influencer Programme
8-15 creators per quarter. Trackable. Capped. Disciplined.
THE INFLUENCER TIER MIX
MEGA (100K+) 0 · SAR 0
We don't use mega-influencers. Too expensive, too generic. Stay disciplined.
MID (40K-100K) 1-2 / qtr · SAR 12-25K each
Trusted KSA food creators with quality engagement (>4%).
MICRO (10K-40K) 5-8 / qtr · SAR 4-12K each
Foodies, families, neighbourhood guides. Highest ROI.
NANO (3K-10K) 3-5 / qtr · SAR 1-3K each
True locals. Often paid in food + small fee. Authentic voice.
THE RULES (NON-NEGOTIABLE)
Every collaboration has a unique tracking code (UTM + loyalty enrolment code).
Visits driven and revenue tagged are reported back to the brand monthly.
Free meals only — no contra-content arrangements without payment.
Influencers must follow brand voice rules. No 'best biryani in the world' superlatives.
We do not pay for follower counts; we pay for engagement and tracked conversion.
Three-month evaluation: any creator below SAR 0.5 cost-per-tracked-visit is paused.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
8 / 18

## Slide 9
Paid Social — SAR 120K, Disciplined
Test, measure, scale only what works. No 'boost post' button.
Meta (IG + FB)
60% / SAR 72K
Goal: Reach + reservation conversions
Targeting: Saudi families 35-55, geo Riyadh + Jeddah
TikTok
20% / SAR 24K
Goal: Brand awareness + youth
Targeting: Saudi & expat 22-35, foodie interests
Google Search
15% / SAR 18K
Goal: High-intent capture
Targeting: 'Indian restaurant Riyadh', 'wedding catering'
Google Display + YouTube
5% / SAR 6K
Goal: Re-targeting visitors
Targeting: Anyone who's visited the Red Chili site or app
⚠ WORKING ASSUMPTION Test small (SAR 500/day max per ad set). Kill anything below 1.5x ROAS within 7 days. Scale winners only after 30 days of stable performance.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
9 / 18

## Slide 10
WhatsApp — The Highest-ROI Channel
Costs ~SAR 0.05 per message. Open rate 95%+. Already integrated in the platform.
RESERVATION CONFIRMATION
Trigger: On booking
“Your table for [date]. Tap to add to calendar.”
Reduces no-shows by ~25%
LOYALTY WELCOME
Trigger: On enrolment
“Welcome to Royalty Club. Your first benefit: [perk]”
Drives 2nd visit within 30 days
WALLET NUDGE
Trigger: Member, no visit 30d
“Hi [name], you have SAR [x] in your wallet. Reserve a table?”
~12% reactivation rate
BIRTHDAY
Trigger: Member's birthday week
“Happy birthday. We've got something for you.”
Highest single-message ROI
CATERING ENQUIRY
Trigger: Catering form submitted
“Got it — Account Manager will call within 1hr”
Sets expectation; reduces drop-off
REVIEW REQUEST
Trigger: 48hr post-visit
“How was it? Tap to leave a Google review.”
Doubles review volume vs no prompt
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
10 / 18

## Slide 11
KPI Framework — How We Measure
Three layers: vanity (track but ignore), engagement (signal), business (truth).
L1 · VANITY
Watch but don't optimise for
Follower count
Reach
Impressions
Likes
L2 · ENGAGEMENT
Signal of content quality
Saves + shares (top signal)
DM enquiries
Profile visits
Story replies
L3 · BUSINESS
What actually matters
Reservations attributed (per week)
Loyalty enrolments via marketing
Catering enquiries received
Cost per acquired customer (CPAC)
Review volume + avg rating
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
11 / 18

## Slide 12
Year-1 Targets — What Success Looks Like
Quarterly stretch + base targets. Honest about ramp.
Metric
Q1
Q2
Q3
Q4
Instagram followers
12K
20K
32K
45K
TikTok followers
5K
12K
22K
35K
Loyalty members (cumulative)
300
750
1,400
2,200
Reservations attributed/wk
15
35
55
80
Catering enquiries/wk
1-2
3-5
5-8
8-12
Google review avg
4.4
4.5
4.5
4.6
⚠ WORKING ASSUMPTION Targets are stretch, not floor. If Q1 is 50% below — that's a signal something is wrong with content or product, not just to spend more. Quarterly review with Dr. Khan to evaluate.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
12 / 18

## Slide 13
Team & RACI
Two FTEs in-house + one external agency partner. Clear ownership, no orphan tasks.
Community Manager
Hire (FTE)
Daily posting · DM responses · Story management · Influencer outreach
Reports to:
Marketing Lead
Content Lead
Hire (FTE)
Calendar · Photography · Video direction · Brand voice gatekeeping
Reports to:
Marketing Lead
Pixel Prism (Agency)
Retainer
Reels production · Photo shoots · Quarterly campaigns · Major creative
Reports to:
Content Lead
Marketing Lead
Dr. Khan / nominee
Strategy · Budget · Approvals · Quarterly review with NTT
Reports to:
Dr. Khan / SPV Board
NTT Intelligence Layer
NTT support
Cross-channel analytics · Attribution · ROI dashboards
Reports to:
Marketing Lead
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
13 / 18

## Slide 14
Brand Guardrails — What We Don't Do
Non-negotiable. No exception even for 'one-off campaigns.'
✗ Use 'best in class' / 'world-class' / superlatives
Lets the customer decide. Self-praise reads as insecurity.
✗ Run discount-led campaigns ('50% off!')
Trains the customer to wait for the next discount. Loyalty club is the lever, not promo prices.
✗ Comment on politics, current affairs, religion
Red Chili is a place. Not a platform. Stay above.
✗ Tag/feature competitors
We don't lift them; we don't punch down. Pretend they don't exist on the feed.
✗ Use stock food photography
Every hero shot is the actual food, made by the actual kitchen, on the actual day.
✗ Promise things we can't deliver
'Ready in 10 minutes' on Friday at 8pm is a lie. Don't post it. Set realistic expectations.
✗ Engage with negative reviews defensively
Acknowledge, apologize for the experience, take it offline. Never argue publicly.
✗ Mass-DM cold prospects
Looks like spam. Damages brand. Use opt-in WhatsApp only.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
14 / 18

## Slide 15
Year-1 Launch Sequence
Quarterly milestones. Each phase has a deliverable and a measurement.
Q1
Foundation
ACTIONS
Hire content lead + community mgr
Photography sprint (40 hero dishes)
Brand voice doc finalised
WhatsApp Business verification
Pixel Prism kickoff
EXIT CRITERIA
Channel infrastructure live
Q2
Awareness
ACTIONS
Daily posting cadence
First influencer cohort (8 creators)
Paid social ramp-up
Loyalty club launch campaign
Catering landing page live
EXIT CRITERIA
Engagement rate >4%, 750 loyalty members
Q3
Conversion
ACTIONS
Reservation campaigns peak
Catering case study series
WhatsApp loyalty wallet active
Review volume push
First quarterly Dr. Khan review
EXIT CRITERIA
55 reservations/wk attributed
Q4
Scale
ACTIONS
Ramadan campaign (cultural moment)
Wedding season catering push
Influencer cohort #2 (different creators)
Google ads expansion
Year-2 plan drafted
EXIT CRITERIA
2,200 loyalty members, 80 res/wk
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
15 / 18

## Slide 16
Marketing Risks — What Could Go Wrong
Four scenarios we plan for now, before they become emergencies.
Content quality is mediocre
Signal: Engagement <2%, low save rates
MITIGATION
Tighten brand voice. Bring in stronger creative direction. Cut output volume, raise quality.
Influencers drive views, not visits
Signal: High reach, low tracked conversion
MITIGATION
Cut underperformers after 3 months. Reallocate to nano-tier (more authentic, lower cost).
Brand reposition fails outside marketing
Signal: Marketing brings traffic, but conversion drops, repeat visits drop
MITIGATION
This is an F&B / service issue, not a marketing one. Escalate to Dr. Khan. Marketing alone can't fix a broken product.
Negative review storm
Signal: Cluster of bad reviews / social calls-out
MITIGATION
Crisis comms playbook activated. Acknowledge publicly, fix privately, share visible improvements.
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
16 / 18

## Slide 17
Next 30 Days — Concrete Marketing Actions
Specific, dated, owned. No 'TBD' on this slide.
Days 1-7
Brand voice doc + content calendar template approved by Dr. Khan
Content Lead (TBH)
Days 1-10
Photography sprint scheduling — 40 hero dishes across 3 branches
Pixel Prism
Days 7-14
Hire community manager + content lead (job spec, interviews, offers)
Marketing Lead
Days 10-20
WhatsApp Business verification + automation flows configured
NTT/VVG
Days 14-21
First influencer cohort identified, contracts drafted (8 creators)
Community Mgr
Days 20-25
Loyalty launch campaign creative ready (in line with Initiative 3 launch)
Pixel Prism + Content Lead
Days 25-30
Quarterly review template + KPI dashboard live in NTT intelligence layer
NTT/VVG
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · CONFIDENTIAL
17 / 18

## Slide 18
Marketing amplifies. It doesn't rescue.
If the food, service, and ambience are right, this strategy delivers. If they're not, no budget can paper over them.
The honest contract:
What the marketing strategy commits to
Disciplined channel mix
Honest measurement
Brand voice protection
Quarterly review with Dr. Khan
What it depends on Dr. Khan to deliver
Ringfenced budget (SAR 720K-960K Yr 1)
F&B / service quality at the branches
Approvals turned around within 5 days
Honesty about what's working / not
Marketing Strategy · Red Chili × Pixel Prism × NTT/VVG · v1.0 Draft
CONFIDENTIAL · For Dr. Sharouz Khan and authorised reviewers only